## FutuRaM: Development Task Force

## Date: 2023-06-20

Participants:

| Empa | ULEI | UNITAR | TUBerlin | Vito |
| --- | --- | --- | --- | --- |
| Joana | Stewart | Tales | Katharina | Christoph |
|  |  |  | Rebecca |  |

- Present

- Excused

- Not present

Agenda:

- Kirsten has asked us to present the task force activities in the next WP1 meeting (next Monday)

  - Explain in a very simple manner what we are doing and why

  - Clarify why we need to build the template for data collection

  - Do the waste streams already know about which data needs to be collected? We need to give an outlook/timeline --> when do we (in particular UNITAR) want to discuss together with the waste streams

  - When do we have a 1st version (provide timeline)

- Discuss Kirsten’s/Katharina's comment "we also need TC for the waste incineration which will be part of the “FutuRaM refining and incineration” model" and adapted diagram

- Discuss the template updates (Rebecca, Tales)

- Discuss aspects raised during the consortium meeting:

- TCs – with regards to each recycling processes / different efficiencies

  - Why not just do one sensitivity analysis?

  - This could be done independently

- FutuRaM – it’s about future --> is there a plan to link the models to the scenario modelling?

- Estimations for future composition …. (next 6 months)

- Look at the regulations and take this into account (Claude - batteries)

- Considerations on data quality (Matthias)

Important documents:

- Slides prepared by Natalie pertaining to the TC: 230523_approachTC.pptx (sharepoint.com)

- Task force folder: M12_transferCoefficients

- Katharina's Flowchart: flow charts_finalized with WS

- Stewart waste treatment process list: shared folder (about 500 processes)

Task force Teams folder: M12_transferCoefficients

Discussion:

- To finalize 1st draft we need:

  - List of processes (end of the week)

  - List of flows (complete 1st draft in the next 2 weeks)

  - PCME list --> code list available already

  - Proposed timeline for 1st data template draft: end of July

    - Tales proposed having some meetings with waste steams after the list of flows is ready to get some initial feedback

- share Monday meeting invitation with Rebecca (DONE)

- During the meeting we discussed the Substances concept as it is defined currently in the model. We agreed upon changing it to PCME (product, compound, material/mineral element) as suggested by Katharina

- Flow splitters were discussed during the meeting. Currently we consider only transformation units in the template (processes)

  - Katharina will also revise the diagrams since some of the splitters represented using an ellipse shape might not be necessary (at least for the moment)

  - The splitter concept is useful for the scenarios specification --> further discussions are needed to understand how those can be incorporated in the template or encoded in scenario definition

- Rebecca asked if she should add the description/definition of the processes to the template. The conclusion was that it should be added and that many of those definitions are standardized already.

Next steps:

- (Joana) send the 1st version of the presentation template by the end of today (2023-06-20)

  - To be reviewed by all

- Discuss Kirsten’s/Katharina's comment "we also need TC for the waste incineration which will be part of the “FutuRaM refining and incineration” model" and adapted diagram

- Discuss the template updates (Rebecca, Tales)

- Discuss aspects raised during the consortium meeting:

  - TCs – with regards to each recycling processes / different efficiencies

    - Why not just do one sensitivity analysis?

    - This could be done independently

  - FutuRaM – it’s about future --> is there a plan to link the models to the scenario modelling?

  - Estimations for future composition …. (next 6 months)

  - Look at the regulations and take this into account (Claude - batteries)