## FutuRaM: Development Task Force

## Date: 2023-06-27

Participants:

| Empa | ULEI | UNITAR | TUBerlin | Vito |
| --- | --- | --- | --- | --- |
| Joana | Stewart | Tales | Katharina | Christoph |
|  |  |  | Rebecca | Lorena |

- Present

- Excused

- Not present

Feedback from WP1_meeting_230626:

- About the timeline, some WS groups (e.g., ELV) cannot provide feedback because most of the members will be on summer vacation.

- Kirsten would like us to present the initial TC template on July 27 or the week after that.

  - Draft template and model mathematical representation

  - Model Mathematical representation will be addressed in the modelling group

- Natalie suggested avoiding the overlap of work from different groups and arranging meetings together with WS groups, development groups, and the TC group. (sometime in mid. July) - involve Nathalie in the prep. for WS feedback collection (~1hr meetings)

  - Sarah has suggested the construction of very focused meetings for the dissemination of the data collection together with industry stakeholders (prepare well for such interactions and ensure we can get concrete feedback)

- Tales will join the future recovery technologies meeting in the afternoon.

  - It was mentioned that looking at and proposing future technologies could be the real contributions of FutuRaM. This should be reflected in the scenario description.

- They are wondering if there are any case studies that can apply to the data gap. Tales mentioned there may be two case studies on WEEE (in AUT and from WEEE Cycling) that should be used to obtain data on transfer coefficients.

- Lucia mentioned she is not so sure calculating TC in every step of each technology is really working/efficient for the model. Jose replied we cannot assess the future only based on understanding the flows. To counter the economic argument, CRMs are currently not economically recovered, but the law says that they have to.

- WP2 member mentioned that it is important to make everyone aware that TCs need to be taken into consideration for the case studies/scenarios work

- UNFC needs the same terminologies (PCME, processes) for its template. Soraya (WP5) asked to share it. The currently available codelists have been shared

- Partners have asked to share proposals for the mathematical approach we plan to adopt for the modelling (including TC specification). This can also help identifying which kind of information is required from WS.

- ORAMA (Orama – Orama (orama-h2020.eu)) and RepTool (News (wf-reptool.org)) were mentioned

  - RepTool: tool from WEE Forum; Rebecca is doing a mapping between the processes and output fraction from RepTool (list of materials)

Agenda:

- Finalized Codelist

  - Process codelist is mostly finalized -

  - How does technology fits the process code list?  (Tales, Rebecca)

- Work on the template together

  - Tales has a discussion with the modelling team on 2023-06-27 and the template used for the case study can serve as starting point

- Discuss Kirsten’s/Katharina's comment "we also need TC for the waste incineration which will be part of the “FutuRaM refining and incineration” model" and adapted diagram

- Discuss the template updates (Rebecca, Tales)

- Discuss aspects raised during the consortium meeting:

- TCs – with regards to each recycling processes / different efficiencies

  - Why not just do one sensitivity analysis?

  - This could be done independently

- FutuRaM – it’s about future --> is there a plan to link the models to the scenario modelling?

- Estimations for future composition …. (next 6 months)

- Look at the regulations and take this into account (Claude - batteries)

- Considerations on data quality (Matthias)

  - Ask Matthias to join to explain what should be considered for the TC specification (Joana ask Matthias)

  - Jose has mentioned that this approach can be challenging – Needs more discussions

- Feedback from the future recovery technologies meeting with Natalie (Tales and Joanna)

  - Link to Maria’s ppt: 20230616_Future-Recovery_Maria.pptx

- Check everyone’s summer vacation for the further meetings.

Important documents:

- Slides prepared by Natalie pertaining to the TC: 230523_approachTC.pptx (sharepoint.com)

- Task force folder: M12_transferCoefficients

- Katharina's Flowchart: flow charts_finalized with WS

- Stewart waste treatment process list: shared folder (about 500 processes)

Task force Teams folder: M12_transferCoefficients

Discussion:

- The timeline for collecting feedback from WS was discussed – we are aware that we need to postpone the meetings with the WS due to holidays. However, for now we keep the timeline as in the ppt presented on 26.06.2023. Once we get the pre-draft version of the template we discuss with Natalie and prepare for the interactions with WS (mid. July). Feedback about composition templates and TC should be collected.

  - This joint approach has been suggested in WP1 meeting (29-06-2023)

- We agreed upon presenting the pre-draft and mathematical model in the next WP meeting. Tales will coordinate this activity with the modelling development team.

- Not clear to anyone how the developed codelist will be used by the UNFC

- Rebecca has showned the progress pertaining to the process codelist. This is mainly finalized.  The categorization of the processes is available at FutuRaM_process_codelists_WP3_draft.xlsx ( tab “diagram”)

- TC for a combination of technologies/processes (e.g.: bottom ash treatment) --> could be added in a level 2 category “recovery processes combination” and then level 3 “bottom ash treatment”

- The processes codelist main categories are based on the waste statistics framework ( presented in slide 6: FutuRaM - Project Overview KB June 23.pptx (sharepoint.com)) currently the graph version is being used. Not clear if this vocabulary is available in other format.

- RepTool was mentioned and Rebecca is mapping the processes and output fraction from RepTool (list of materials) --> Home (wf-reptool.org), 230531_RepTool output lists for CRM_mappingCodelist.xlsx

  - Alignment with ecoinvent seems to be more complex

- Huge tables with (harmonized) vocabulary are been developed

  - How does FutuRaM KB use it? -> it was mentioned that there is lack of communication between WP4 (model) and WP6 (KB)

    - Essentially results from the model are stored in the KB --> how to trace back the model assumptions and input specifications?

- The data quality approach has been discussed --> we should spend more time understanding how we can implement it. Katharina has suggested to invite Matthias to one of the Tue meetings (added to the action points). The scoring and pedigree matrix approach were briefly mentioned. --> more clarity is needed

Next steps:

- Katharina is updating the flowcharts

- Joana looks into the graph tools (check Stewart code in github) and ask Matthias about availability to attend Tue meeting to discuss the data quality assessment approach

- Rebecca and Tales --> work on the codelist for process and think on how to integrate the technologies

- Tales will discuss further the small example in the modelling group. This example will be used as basis for the next meeting where we will work on the TC template together.

Summer Vacation:

- Tales: 29-30 June, 13-14 July, 4-11 August

- Katharina: 04-05 July; 31 July – 09 August

- Joana: 09-28 August (tentative)

- Rebecca: 10-11, 24-28 July

- Stewart